## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 | 8 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | Done
Task | Created guest checkout model and schema | Roland | 4 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Created and Updated all endpoints. Create, Read, Update and Delete all done | Roland | 3 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | All Pytest for guest checkout is done | Roland | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
User Story #2 | 3 | Preston | 8 | 2 | 0 | 0 | 0 | 7 | 0 | To Do
Task | Create nested menu that has categories (Already done via menu_items schema and model) | Preston | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | endpoints (GET, PUT, DELETE, POST) | Preston | 3 | 1 | 0 | 0 | 0 | 3 | 0 | Done | 0
Task | Pyunit Tests | Preston | 2 | 0 | 0 | 0 | 0 | 2 | 0 | Done
Task | api for functionality (get an item, display menu, create a menu item, etc..) | Preston | 3 | 1 | 0 | 0 | 0 | 2 | 0 | Done | 0
User Story #9 & #10 | 5 |  | 5 | 2 | 0 | 1 | 0 | 0 | 0 | To Do
Task | Create models and schemas for System Documentation and Data Analysis | Cesar | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Make Endpoints for System Documentation and Data Analysis | Cesar | 2 | 1 | 0 | 1 | 0 | 0 | 0 | Done | 0
Task | Make Pytest for System Documentation and Data Analysis | Cesar | 2 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Task |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
User Story #4 | 8 |  | 8 | 2 | 2 | 2 | 1 | 0 | 1 | To Do
Task | Created the payment Model and Schemas with its relationship to Orders | Lauren | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Created Endpoints for payment processing (POST, GET, PUT, DELETE) | Lauren | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Done | 0
Task | Implemented submit_payment() function to validate card information and store for future use | Lauren | 3 | 1 | 0 | 2 | 0 | 0 | 0 | Done | 0
Task | Pyunit Tests for payment processing | Lauren | 2 | 0 | 0 | 0 | 1 | 0 | 1 | Done | 0
User Story #5 | 3 |  | 9 | 2 | 1 | 2 | 3 | 1 | 0 | To Do
Task | Create models and schemas for order_tracking | Alex | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Add api endpoints for tracking orders | Alex | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 0
Task | Implement logic to calculate ready time | Alex | 4 | 0 | 0 | 2 | 3 | 0 | 0 | Done | 0
Task | PyTests | Alex | 2 | 0 | 0 | 0 | 0 | 1 | 0 | To Do | 0
TOTAL |  |  | 38 | 8 | 3 | 5 | 4 | 8 | 1 |  | 14