## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #3 |  | Cesar | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done
Task | Give the user the option of Delivery or Takeout |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Assign order id to every new order |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Done | 0
Task |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
User Story #7 |  | Alex | 1 | 2 | 1 | 0 | 0 | 4 | 0 | To Do
Task | Create modes and schemas for customer feedback |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Add API endpoints for customers to submit feedback |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 0
Task |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Doing
Task | write pytests for customer feedback |  | 0 | 1 | 0 | 0 | 0 | 2 | 0 | Doing | 0
User Story #8 |  | Roland | 12 | 2 | 0 | 1 | 0 | 0 | 0 | To Do
Task | Created models and schemas for adding promo codes to orders |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 0
Task | Added API endpoints for creating and modifying new promo orders |  | 5 | 1 | 0 | 1 | 0 | 0 | 0 | Done | 0
Task | Finished logic to tie promo codes to individual orders |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
Task | Wrote py tests for each end point |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | To Do | 0
TOTAL |  |  | 15 | 5 | 2 | 1 | 0 | 4 | 0 |  | 14